## Blank timeline
Project timeline
Enter tasks, owners and dates. The timeline fills automatically.
| First day shown |  | 2026-09-14 |  |  |  |  | 2026-09-14
ID | Task | Owner | Start | Finish | Days | Status | Depends on | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-04 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-11
Yellow cells are editable. Days includes the start and finish date.
Depends on records task IDs. Changing a dependency does not move dates.
HYPERLINK is not implemented. linkLocation=https://tooling.studio/kanban-tasks?utm_source=timeline-template&utm_medium=resource, friendlyName=Use a shared board and Gantt view in Kanban Tasks

## Example timeline
Project timeline
Example project. Replace these tasks with your own.
| First day shown |  | 2026-09-14 |  |  |  |  | 2026-09-14
ID | Task | Owner | Start | Finish | Days | Status | Depends on | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-04 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-11
1 | Agree the project brief | Alex | 2026-09-14 | 2026-09-15 | 2 | Done | bar: 2026-09-14 to 2026-09-15
2 | Plan tasks and owners | Sam | 2026-09-16 | 2026-09-17 | 2 | In progress | 1 | bar: 2026-09-16 to 2026-09-17
3 | Prepare the first draft | Jordan | 2026-09-18 | 2026-09-22 | 5 | Not started | 2 | bar: 2026-09-18 to 2026-09-22
4 | Review with the team | Alex | 2026-09-23 | 2026-09-24 | 2 | Not started | 3 | bar: 2026-09-23 to 2026-09-24
5 | Make final changes | Jordan | 2026-09-25 | 2026-09-28 | 4 | Not started | 4 | bar: 2026-09-25 to 2026-09-28
6 | Approve and launch | Sam | 2026-09-29 | 2026-09-30 | 2 | Not started | 5 | bar: 2026-09-29 to 2026-09-30
Yellow cells are editable. Days includes the start and finish date.
Depends on records task IDs. Changing a dependency does not move dates.
HYPERLINK is not implemented. linkLocation=https://tooling.studio/kanban-tasks?utm_source=timeline-template&utm_medium=resource, friendlyName=Use a shared board and Gantt view in Kanban Tasks